## Sheet1
Requirement ID | Description | Story Points | Priority | Sprint Number
1 | Set up project repository and environment (e.g., Node.js, React, database) | 2 | High
1.1 | Configure version control with Git and CI/CD pipeline | 3 | Medium
2 | Design basic app architecture (frontend-backend separation, WebSocket handling, etc.) | 5 | High
2.1 | Define database schema for users, messages, and rooms | 3 | High
2.2 | Create backend API structure (Express/FastAPI/etc.) | 3 | High
3 | Implement WebSocket server for real-time messaging | 8 | High
3.1 | Enable multiple users to connect simultaneously | 5 | High
3.2 | Handle user join/leave notifications | 3 | Medium
3.3 | Implement broadcast of messages to all connected clients | 4 | High
4 | Develop frontend chat interface (message input, message list, user list) | 8 | High
4.1 | Display timestamps and usernames alongside messages | 3 | Medium
4.2 | Auto-scroll chat window on new messages | 2 | Medium
5 | Add ability to create/join named chatrooms | 5 | High
5.1 | Support dynamic room creation and destruction | 4 | Medium
5.2 | Show active room and participant list | 3 | Medium
6 | Implement user identity (temporary usernames or login) | 5 | High
6.1 | Allow users to set/change display names | 3 | Medium
6.2 | Optionally support persistent user accounts with authentication | 8 | Low
7 | Implement message persistence (save chat history to database) | 6 | Medium
7.1 | Load previous messages when joining a room | 4 | Medium
8 | Add moderation features (mute, kick, delete message) | 8 | Low
8.1 | Add profanity filter or content moderation | 5 | Low
9 | Create responsive and accessible UI design | 4 | High
9.1 | Add basic dark/light mode toggle | 3 | Low
10 | Add typing indicators (“User is typing…”) | 4 | Medium
11 | Add connection status indicators (online/offline, reconnecting) | 3 | Medium
12 | Integrate basic analytics (number of active users, messages per room) | 4 | Low
13 | Write unit and integration tests (backend + frontend) | 8 | High
14 | Conduct load testing for concurrency and performance | 5 | Medium
15 | Deploy to production environment (e.g., Vercel + Node backend, or Docker setup) | 5 | High
15.1 | Set up domain and SSL (HTTPS) | 3 | High
16 | Add user feedback or bug report form | 2 | Low
17 | Post-launch monitoring and maintenance plan | 3 | Medium