## Sheet1
Requirement ID | Description | Story Points | Priority | Sprint Number
1 | Set up project repository and environment (Python Backend) | 2 | 1 | 1
1.1 | Configure version control with Git and CI/CD pipeline | 3 | 2 | 1
2 | Design basic app architecture (frontend-backend separation, WebSocket handling, etc.) | 5 | 3 | 1
2.1 | Define database schema for users, messages, and rooms | 3 | 4 | 2
2.2 | Create backend API structure (FastApi) | 3 | 5 | 2
3 | Implement WebSocket server for real-time messaging | 8 | 6 | 2
3.1 | Enable multiple users to connect simultaneously | 5 | 7
3.2 | Handle user join/leave notifications | 3 | 8
3.3 | Implement broadcast of messages to all connected clients | 4 | 9 | 2
4 | Develop frontend chat interface (message input, message list, user list) | 8 | 10 | 2
4.1 | Display timestamps and usernames alongside messages | 3 | 11
4.2 | Auto-scroll chat window on new messages | 2 | 12
5 | Add ability to create/join named chatrooms | 5 | 13
5.1 | Support dynamic room creation and destruction | 4 | 14
5.2 | Show active room and participant list | 3 | 15
6 | Implement user identity (temporary usernames or login) | 5 | 16
6.1 | Allow users to set/change display names | 3 | 17
6.2 | Optionally support persistent user accounts with authentication | 8 | 18
7 | Implement message persistence (save chat history to database) | 6 | 19
7.1 | Load previous messages when joining a room | 4 | 20
8 | Add moderation features (mute, kick, delete message) | 8 | 21
8.1 | Add profanity filter or content moderation | 5 | 22
9 | Create responsive and accessible UI design | 4 | 23
9.1 | Add basic dark/light mode toggle | 3 | 24
10 | Add typing indicators (“User is typing…”) | 4 | 25
11 | Add connection status indicators (online/offline, reconnecting) | 3 | 26
12 | Integrate basic analytics (number of active users, messages per room) | 4 | 27
13 | Write unit and integration tests (backend + frontend) | 8 | 28
14 | Conduct load testing for concurrency and performance | 5 | 29
15 | Deploy to production environment (e.g., Vercel + Node backend, or Docker setup) | 5 | 30
15.1 | Set up domain and SSL (HTTPS) | 3 | 31
16 | Add user feedback or bug report form | 2 | 32
17 | Post-launch monitoring and maintenance plan | 3 | 33